## Plan vs Real
ID | Work Package | Task | Resp. | Plan. Start | Plan. Finish | Real Start | Real Finish | Re-planned finish | Delay (working days) | Status | Notes (why)
1.1 | WP1 | Repository set-up and structure | Deolinda | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-10-12 |  | 17 | Completed | Repo created on 17/09, but the folders only got the required names (report/, status/, gantt/, references/) on 12/10, after reviewing the formal requirements. Final clean-up on 25/10 (old drafts and non-source files removed).
1.2 | WP1 | Role and section assignment | All | 2026-10-07 | 2026-10-07 | 2026-10-07 | 2026-10-07 |  | 0 | Completed | Roles confirmed by all members on 07/10, as planned. Sections were re-assigned on 22/10 (see Events).
1.3 | WP1 | Gantt chart v1 + risk analysis (delivery) | Biel | 2026-10-07 | 2026-10-09 | 2026-10-07 | 2026-10-12 |  | 1 | Completed | Delivered on time (09/10, 11:38). Corrected on 12/10 after the lecturer's feedback, so the task closed 1 working day late. The corrected v1 is in gantt/ (gantt-v1-delivered-corrected).
2.1 | WP2 | Initial paper scan | All | 2026-09-20 | 2026-09-27 | 2026-09-30 | 2026-10-01 |  | 4 | Completed | Started 10 days late: the first weeks went into setting up the repository and understanding the project brief. Shared notes file created on 30/09.
2.2 | WP2 | Literature search on MODY2 and GCK (PDFs in references/) | All | 2026-10-07 | 2026-10-14 | 2026-10-08 | 2026-10-25 |  | 7 | Completed | Most PDFs were added on 19/10 (Biel 6, Unai 2, Maeve 1). The key primary paper on our variant (Liu 2011) was only found on 21/10 and deposited on 22/10; Madeira 2024 (EMBOSS) on 24/10; the class conservation report (source of the Xenopus data) on 25/10. On 25/10 the folder was cleaned: only sources that the report cites were kept (a search-engine capture, a notes file and two redundant reviews, Matschinsky 1990 and Zhang 2023, were removed).
2.3 | WP2 | Reference log in Mini Oxford style | Deolinda | 2026-10-15 | 2026-10-16 | 2026-10-08 | 2026-10-26 |  | 6 | Completed | A citations file exists since 08/10, but references were in mixed formats (Mini Oxford, URLs, PMIDs). The file was cleaned on 25/10 (Biel). On the morning of 26/10 the reference list of Paper.md still had only Liu 2011 and Kamata 2004: it is completed during the final review (4.6).
3.1 | WP3 | Retrieve human GCK gene and protein | Maeve and Unai | 2026-10-09 | 2026-10-09 | 2026-10-08 | 2026-10-15 |  | 4 | Completed | Gene/protein questions answered on 08/10; NCBI dataset for GCK added on 15/10.
3.2 | WP3 | Characterise the variant | Maeve and Unai | 2026-10-09 | 2026-10-13 | 2026-10-15 | 2026-10-25 |  | 8 | Completed | INCIDENT (solved): the first analysis (Questions.md, 15/10) described a different substitution (c.388A>G). At the tutoring on 21/10 we compared the WT and mutant FASTA files of MODY2.zip again: the real variant is c.1015G>A, p.Glu339Lys (E339K). The genomic characterisation (codon GAG>AAG, transition, missense, charge reversal) was written as a Results subsection on 25/10 (Deolinda, revised by Ariadna). 8 working days late.
3.3 | WP3 | Select comparison species | Ari and Biel | 2026-10-09 | 2026-10-09 | 2026-10-15 | 2026-10-15 |  | 4 | Completed | Ovis aries (close mammal) and Xenopus laevis (distant vertebrate) retrieved on 15/10 with BLAST (NCBI RefSeq NP_001274400.1 for sheep), 4 working days later than planned. On 22/10 the group considered dropping Ovis aries for lack of time; after re-reading the brief ('at least 2 other relevant species') it was kept on 23/10.
3.4 | WP3 | Pairwise and multiple sequence alignment | Maeve / Biel | 2026-10-15 | 2026-10-19 | 2026-10-22 | 2026-10-23 |  | 4 | Completed | Delayed because the team prioritised the Background draft. Done in two parts: human vs Xenopus from the conservation report generated in class (22/10; 80.6% identity, 88.4% same physicochemical group) and human vs Ovis aries with EMBOSS Needle (23/10, Biel; 96.6% identity, 98.3% similarity, 0 gaps). Residue 339 is E in the three species. The Needle output was re-uploaded to references/ on 25/10, after the data/ folder was removed.
3.5 | WP3 | Structural analysis (PDB) | Unai | 2026-10-14 | 2026-10-16 | 2026-10-19 | 2026-10-25 |  | 5 | Completed | Reference structures 1V4S/1V4T identified on 19/10. On 21/10 we found an experimental structure of our mutant (PDB 3QIC), so risk R3 did not happen. The structural and kinetic analysis of E339K (Liu 2011 + class superposition) was finally written by Ariadna (24-25/10) and its method by Ariadna (25/10); Unai contributed the clinical/pregnancy text instead (25-26/10). 5 working days late.
3.6 | WP3 | Structure superposition healthy vs variant | All (class session) | 2026-10-22 | 2026-10-23 | 2026-10-22 | 2026-10-22 |  | -1 | Completed | Done in the 22/10 class session: the conservation report includes the WT vs E339K superposition (global RMSD 1.48 A; 2.49 A at residue 339) and the human vs Xenopus superposition (global RMSD 8.18 A, one domain displaced as a block). Interpreted the same day with the lecturer using Liu 2011 (PDB 3QIC).
4.1 | WP4 | Background section | Ari | 2026-10-14 | 2026-10-19 | 2026-10-19 | 2026-10-25 |  | 4 | Completed | Drafts written in borrador/ (19-22/10) by four members, partly in Spanish. On 24/10 Ariadna created borrador/Paper.md as the single final document. On 25/10 Maeve rewrote the MODY2/GCK background and the separate 'Physiology of wild-type glucokinase' subsection (Biel, 19-24/10) was condensed into the Background (Ariadna) to keep one introduction within the length limit. Aims of the study added at the end.
4.2 | WP4 | Methods section | Biel | 2026-10-14 | 2026-10-16 | 2026-10-24 | 2026-10-25 |  | 5 | Completed | Could not be written before the analyses (3.4-3.6). Started on 24/10 by Biel (EMBOSS Needle parameters, source of the Xenopus data); completed on 25/10 by Deolinda (sequence sources, BLASTn, order of paragraphs) and Ariadna (PDB search, superposition, data taken from Liu 2011).
4.3 | WP4 | Results section | Maeve | 2026-10-20 | 2026-10-26 | 2026-10-23 | 2026-10-25 |  | 0 | Completed | Three subsections: species comparison + Table 1 (Biel, 24/10), genomic characterisation of E339K (Deolinda/Ariadna, 25/10) and structural and kinetic impact (Ariadna/Maeve, 24-25/10). Headings reorganised into the BMC structure on 25/10 (Biel, Deolinda). Finished the day before the planned date.
4.4 | WP4 | Discussion and Conclusions | Unai | 2026-10-20 | 2026-10-23 | 2026-10-25 | 2026-10-26 |  | 1 | Completed | Re-planned after Results. Discussion started by Deolinda (25/10) and rewritten by Maeve (26/10); a second version was drafted in parallel in a shared document, and both are merged during the final review. Conclusions written on 26/10. 1 working day late.
4.5 | WP4 | Abstract and keywords | Deolinda | 2026-10-26 | 2026-10-26 | 2026-10-24 | 2026-10-25 |  | 0 | Completed | Started on 24/10 and finished on 25/10 ('Final revision for abstract'), one day earlier than planned; it is checked against the final Discussion during 4.6.
4.6 | WP4 | Format and citation review | All | 2026-10-26 | 2026-10-26 | 2026-10-26 |  | 2026-10-26 | 0 | In progress | 26/10, final review before the internal deadline (18:00; Atenea closes at 22:00). Merge of the two Discussion versions, complete reference list, remaining [CITATION] marks, BMC section order and English language check. No questions are answered by the lecturers on 26/10.
5.1 | WP5 | Live Gantt update and retrospective | Biel and Deolinda | 2026-10-10 | 2026-10-22 | 2026-10-22 | 2026-10-26 |  | 2 | Completed | The live status document was only created on 22/10 (planned from 10/10). Gantt v2, this status document and the retrospective were prepared on 22/10, updated on 24/10 and finalised on 26/10 from the commit history.
5.2 | WP5 | Defence preparation, all sections | All | 2026-10-27 | 2026-11-03 | 2026-10-23 |  | 2026-11-03 | 0 | In progress | Unchanged. Every member must be able to explain every section (not only their own).

## Timeline
ID | Task | Row | 15/09 | 16/09 | 17/09 | 18/09 | 19/09 | 20/09 | 21/09 | 22/09 | 23/09 | 24/09 | 25/09 | 26/09 | 27/09 | 28/09 | 29/09 | 30/09 | 01/10 | 02/10 | 03/10 | 04/10 | 05/10 | 06/10 | 07/10 | 08/10 | 09/10 | 10/10 | 11/10 | 12/10 | 13/10 | 14/10 | 15/10 | 16/10 | 17/10 | 18/10 | 19/10 | 20/10 | 21/10 | 22/10 | 23/10 | 24/10 | 25/10 | 26/10 | 27/10 | 28/10 | 29/10 | 30/10 | 31/10 | 01/11 | 02/11 | 03/11 | 04/11 | 05/11
1.1 | Repository set-up and structure | Planned
1.1 |  | Real
1.2 | Role and section assignment | Planned
1.2 |  | Real
1.3 | Gantt chart v1 + risk analysis (delivery) | Planned
1.3 |  | Real
2.1 | Initial paper scan | Planned
2.1 |  | Real
2.2 | Literature search on MODY2 and GCK (PDFs in references/) | Planned
2.2 |  | Real
2.3 | Reference log in Mini Oxford style | Planned
2.3 |  | Real
3.1 | Retrieve human GCK gene and protein | Planned
3.1 |  | Real
3.2 | Characterise the variant | Planned
3.2 |  | Real
3.3 | Select comparison species | Planned
3.3 |  | Real
3.4 | Pairwise and multiple sequence alignment | Planned
3.4 |  | Real
3.5 | Structural analysis (PDB) | Planned
3.5 |  | Real
3.6 | Structure superposition healthy vs variant | Planned
3.6 |  | Real
4.1 | Background section | Planned
4.1 |  | Real
4.2 | Methods section | Planned
4.2 |  | Real
4.3 | Results section | Planned
4.3 |  | Real
4.4 | Discussion and Conclusions | Planned
4.4 |  | Real
4.5 | Abstract and keywords | Planned
4.5 |  | Real
4.6 | Format and citation review | Planned
4.6 |  | Real
5.1 | Live Gantt update and retrospective | Planned
5.1 |  | Real
5.2 | Defence preparation, all sections | Planned
5.2 |  | Real
Planned (Gantt v1)
Real (from commits)
Real, task with incident
Re-planned (forecast)
Weekend