## Cover
DISEASE PROJECT · GROUP 12DP-B
MODY2: Molecular Basis of a Monogenic Diabetes
Sequence, structure and cross-species comparison of human glucokinase (GCK)
GENERAL OBJECTIVE
To characterise how a disease-causing mutation in the human GCK gene reshapes the structure and function of glucokinase, and how this molecular change ultimately gives rise to the observable phenotype of GCK-MODY.
SPECIFIC OBJECTIVES
1. | Retrieve and validate the reference and disease-associated GCK gene/protein sequences.
2. | Characterise the effect of the assigned variant at sequence level.
3. | Compare human GCK with Xenopus laevis and ≥ 1 further species; assess conservation.
4. | Interpret the variant in the 3D structure of glucokinase.
5. | Integrate the findings into a BMC-format report and defend it orally.
MILESTONES
M1 | M2 | M3 | M4
Gantt chart delivered | Status retrospective | Final report submitted | Oral defence
09/10/26 | 22/10/26 | 26/10/26 | 05/11/26
WORK PACKAGES
WP | Name |  | Owner | Start | End
WP1 | Repository & Setup |  | Biel | 17/09/26 | 09/10/26
WP2 | Literature Review |  | Ari | 20/09/26 | 16/10/26
WP3 | Bioinformatic Analysis |  | Unai | 09/10/26 | 23/10/26
WP4 | Report Writing |  | Maeve | 14/10/26 | 26/10/26
WP5 | Status Review & Defence |  | Deolinda | 10/10/26 | 03/11/26
PROJECT | Whole project |  | — | 17/09/26 | 03/11/26
PROJECT TEAM
Name | Role | Responsibility |  | Background
Biel | Repository & Setup Owner | Creates/maintains the GitHub repo; owns WP1 setup. |  | 1st-year Bioinformatics student
Deolinda | Planning Lead | Owns the Gantt chart (v1 and the live v2 retrospective); owns WP5 (Status Review & Defence). |  | 1st-year Bioinformatics student
Ari | Literature & Species Lead | Leads literature search and cross-species comparison; owns WP2 (Literature Review). |  | 1st-year Bioinformatics student
Maeve | Analysis Support | Supports sequence/structure analysis and the written report; owns WP4 (Report Writing). |  | 1st-year Bioinformatics student
Unai | Bioinformatic Analysis Lead | Leads sequence retrieval, variant and structural analysis; owns WP3 (Bioinformatic Analysis). |  | 1st-year Bioinformatics student

## Gantt Chart
ID | Work Package | Task | Owner | Output | Duration (working days) | Pred. | Accomplished when | Comments/status | Start | End
1.1 | WP1 | Repository set-up and structure | Deolinda | Repo with folder structure | 1 | — | All members can push |  | 2026-09-17 | 2026-09-17
1.2 | WP1 | Role and section assignment | All | Owner lines agreed | 1 | 1.1 | Every section has an owner | Biel–repo/WP1, Deolinda–Gantt chart, Ari–literature, Maeve–analysis support, Unai–bioinformatics (all confirmed 07/10). | 2026-10-07 | 2026-10-07
1.3 | WP1 | Finish the gantt and deliver it | Biel | Gantt chart (PDF/XLSX) in /gantt folder | 3 | 1.2 | Delivered before 09.10 22:00 |  | 2026-10-07 | 2026-10-09
WP1 TOTAL | [8 empty] | 2026-09-17 | 2026-10-09
2.1 | WP2 | Initial paper scan | All | Shortlist of candidate papers | 4 | — | Each member has skimmed a few candidate papers on MODY2/GCK |  | 2026-09-20 | 2026-09-27
2.2 | WP2 | Literature search on MODY2 and GCK | All | PDFs in references/ | 5 | 2.1 | ≥8 sources, reviews/originals separated | Biel–pregnancy/GCK paper, Deolinda–MODY rapid review, Ari–citation review, Maeve–GCK mutations + precision diabetes papers, Unai–treatment options paper. | 2026-10-07 | 2026-10-14
2.3 | WP2 | Reference log with citation style | Deolinda | Reference log table | 2 | 2.2 | Every source cited in Mini Oxford style |  | 2026-10-15 | 2026-10-16
WP2 TOTAL | [8 empty] | 2026-09-20 | 2026-10-16
3.1 | WP3 | Retrieve human GCK gene and protein | Maeve and Unai | Accession list + FASTA | 1 | — | Sequences match MODY2.zip |  | 2026-10-09 | 2026-10-09
3.2 | WP3 | Select and justify the disease variant | Maeve and Unai | Variant sheet | 2 | 3.1 | Variant chosen with written rationale |  | 2026-10-09 | 2026-10-13
3.3 | WP3 | Select comparison species | Ari and Biel | Species table with justification | 1 | 3.1 | X. laevis included, others justified |  | 2026-10-09 | 2026-10-09
3.4 | WP3 | Pairwise and multiple sequence alignment | Maeve | Alignment files + figure | 3 | 3.3 | Conservation of mutated position assessed | Maeve: retrieves orthologous sequences for X. laevis + 2nd species (15/10), pairwise BLAST alignment vs. human GCK (16/10), then MSA + conservation figure (19/10). | 2026-10-15 | 2026-10-19
3.5 | WP3 | Structural analysis (PDB / AlphaFold) | Unai | Structure figure | 3 | 3.2 | Variant position located in structure |  | 2026-10-14 | 2026-10-16
3.6 | WP3 | Structure superposition healthy vs variant | Ari | Superposition figure | 2 | 3.5 | Structural consequence described |  | 2026-10-22 | 2026-10-23
WP3 TOTAL | [8 empty] | 2026-10-09 | 2026-10-23
4.1 | WP4 | Background section | Ari | Background section | 4 | 2.2 | Within agreed length, fully cited | Ari drafts disease background first (14–15/10), then gene/protein background (16–19/10). | 2026-10-14 | 2026-10-19
4.2 | WP4 | Methods section | Biel | Methods section | 3 | 3.2 | Reproducible: sources, tools, parameters |  | 2026-10-14 | 2026-10-16
4.3 | WP4 | Results section | Maeve | Results section (≤5 figures) | 5 | 3.4 | Findings only, no interpretation | Maeve drafts sequence/variant results first (20–21/10), then alignment/conservation results (22–23/10), then structural results once the 22.10 lab is done (26/10). | 2026-10-20 | 2026-10-26
4.4 | WP4 | Discussion and Conclusions | Unai | Discussion & Conclusions | 4 | 3.4 | Answers the project question | Unai interprets sequence + alignment findings together (20–21/10), then relates them to clinical phenotype and states limitations (22–23/10). | 2026-10-20 | 2026-10-23
4.5 | WP4 | Abstract and keywords | Deolinda | Abstract (≤350 words) | 1 | 4.3, 4.4 | Background/Results/Conclusions structure |  | 2026-10-26 | 2026-10-26
4.6 | WP4 | Format and citation review | All | Final report.md | 1 | 4.5 | ≤7 pages/5000 words, ≤5 figures, style ok | Each member reviews their own section: Deolinda–Overview/Abstract, Maeve–Methods/Gantt, Ari–Background/citations, Unai–Discussion/Conclusions, Biel–Results/figures. | 2026-10-26 | 2026-10-26
WP4 TOTAL | [8 empty] | 2026-10-14 | 2026-10-26
5.1 | WP5 | Live Gantt update and retrospective | Biel | Gantt v2 + gap analysis | 8 | — | Differences v1 vs v2 explained; tracked continuously since M1 |  | 2026-10-10 | 2026-10-22
5.2 | WP5 | Defence preparation, all sections | All | Shared defence notes | 6 | 4.6 | Every member can explain every section | Deolinda–Overview/Background, Maeve–Methods/Gantt retrospective, Ari–species comparison/conservation, Unai–Discussion/Conclusions, Biel–Results/structural analysis. | 2026-10-27 | 2026-11-03
WP5 TOTAL | [8 empty] | 2026-10-10 | 2026-11-03
PROJECT TOTAL | [8 empty] | 2026-09-17 | 2026-11-03
Durations are given in working days (Mon–Fri); weekends and local holidays (24/09, 12/10 and 01/11) are excluded.

## Timeline
PROJECT TIMELINE
ID | Task | Owner | SEPTEMBER | [13 empty] | OCTOBER | [30 empty] | NOVEMBER
|  |  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5
1.1 | Repo with folder structure | Deolinda | bar: SEPTEMBER 17
1.2 | Owner lines agreed | All | bar: OCTOBER 7
1.3 | Gantt chart (PDF/XLSX) in /gantt folder | Biel | bar: OCTOBER 7 to OCTOBER 9
2.1 | Shortlist of candidate papers | All | bar: SEPTEMBER 20 to SEPTEMBER 27
2.2 | PDFs in references/ | All | bar: OCTOBER 7 to OCTOBER 14
2.3 | Reference log table | Deolinda | bar: OCTOBER 15 to OCTOBER 16
3.1 | Accession list + FASTA | Maeve and Unai | bar: OCTOBER 9
3.2 | Variant sheet | Maeve and Unai | bar: OCTOBER 9 to OCTOBER 13
3.3 | Species table with justification | Ari and Biel | bar: OCTOBER 9
3.4 | Alignment files + figure | Maeve | bar: OCTOBER 15 to OCTOBER 19
3.5 | Structure figure | Unai | bar: OCTOBER 14 to OCTOBER 16
3.6 | Superposition figure | Ari | bar: OCTOBER 22 to OCTOBER 23
4.1 | Background section | Ari | bar: OCTOBER 14 to OCTOBER 19
4.2 | Methods section | Biel | bar: OCTOBER 14 to OCTOBER 16
4.3 | Results section (≤5 figures) | Maeve | bar: OCTOBER 20 to OCTOBER 26
4.4 | Discussion & Conclusions | Unai | bar: OCTOBER 20 to OCTOBER 23
4.5 | Abstract (≤350 words) | Deolinda | bar: OCTOBER 26
4.6 | Final report.md | All | bar: OCTOBER 26
5.1 | Gantt v2 + gap analysis | Biel | bar: OCTOBER 10 to OCTOBER 22
5.2 | Shared defence notes | All | bar: OCTOBER 27 to NOVEMBER 3
| Milestones |  | OCTOBER 9: M1; OCTOBER 22: M2; OCTOBER 26: M3; NOVEMBER 5: M4
| Legend: | WP1 | SEPTEMBER 17: WP2; SEPTEMBER 18: WP3; SEPTEMBER 19: WP4; SEPTEMBER 20: WP5; SEPTEMBER 21: weekend/holiday

## Risk Matrix
RISK MATRIX
Impact → / Likelihood ↓
| I=1 | I=2 | I=3
L=3 |  |  | R1
L=2 |  | R2 R3 R5
L=1 |  |  | R4
| ID | Risk | Why | L | I | Score | Category | Contingency
| R1 | Superposition lab (22.10) leaves very little buffer before the final report deadline (26.10) | Because the superposition technique is only taught in the 22/10 lab (separate from the 01/10 PDB lab), only working days remain before the 26/10 deadline | 3 | 3 | 9 | High | Draft Results/Discussion with alignment data first (ready 19.10); keep the structural superposition as a block added last, once the lab is done
| R2 | Merge conflicts in the shared GitHub repository when several members edit the same files at once | Because 5 people contribute to report.md and related files without a strict branching workflow, concurrent edits are likely to collide | 2 | 2 | 4 | Medium | One file/section per person; use pull requests for review; resolve conflicts promptly as a team instead of editing the same file simultaneously
| R3 | No experimental PDB structure available for the chosen variant | Because not every GCK variant has a solved experimental structure deposited in the PDB | 2 | 2 | 4 | Medium | Use an AlphaFold prediction and state the limitation explicitly in the report
| R4 | Sequence retrieved does not match the provided MODY2.zip | Because public databases (NCBI/Ensembl) may use a different reference transcript/isoform than the one provided in MODY2.zip | 1 | 3 | 3 | Medium | Use MODY2.zip sequences as reference and document the discrepancy
| R5 | A member is ill or unavailable during the final week | Because the final week concentrates several dependent deliverables (report, defence prep), so any absence has high impact | 2 | 2 | 4 | Medium | All work lives on GitHub from day one, so anyone can pick up a section
Score = Likelihood × Impact ¦ Low < 3 Medium 3–5 High > 5